## Product Backlog
Product Backlog
Prioritized High-Level User Story List
User Story ID | Priority | Size | As a(n) <type of user> | I want to <perform some task> | So that I can <achieve some goal>.
1 | 1 | Medium | End User | Click a link to view the top five destinations list | See the most popular locations for travel to educate myself on the best places to go.
2 | 2 | Medium | End User | View top destinations list based on previous vacations of user | Find destinations I would be interested in visiting.
3 | 3 | Medium | End User | Have a profile setting for cruises | Easily view cruise vacation packages
4 | 4 | Large | End User | Have a choice of vacation type | Chose between vacation packages based on desired activities
5 | 5 | Small | End User | Have a filter for price limits | View vacation packages based on a specific budget
6 | 6 | Large | End User | View a list of hot deals based on profiles | See top vacation packages that appeal to me for cheaper prices

## User Story Details Example
User Story Number: | 1
User Story Name: | Top Five Destination List
User Story Size: | Medium
User Story Value Statement: | As an end user, I want to click a link to view the top five destinations list, so that I can see the most popular locations for travel to educate myself on the best places to go.
Acceptance Criteria: | • Ability to click link that takes user to a page displaying top destinations • Ordered list of destinations from the most popular location to the fifth-most popular • Each destination on the list will have the following attributes shown: • Destination name • Destination short description (one sentence) • Destination picture • Text with embedded link to take user to top-selling travel package for that location

## User Story Details #1
User Story Number: | 6
User Story Name: | Hot deals based on profile
User Story Size: | Large
User Story Value Statement: | As an end user, I want to view a list of hot deals based on my profile so that I can see top vacation packages that appeal to me for a cheaper price.
Acceptance Criteria: | • Keep a log of viewed, selected, and purchased vacations by the user • Make hot deals link available at the search page • Compile purchased vacations with viewed vacations to determine similar destinations and vacation types • Compare and display similar vacations currently available in hot deals • Hot deals page will consist of: • A minimum of 5 vacation destinations • List the normal vacation price along with the deal price • Remaining time the deal will be offered • Link to bring user to vacation purchace page with listed deal price

## User Story Details #2
User Story Number: | 3
User Story Name: | Cruise option
User Story Size: | Medium
User Story Value Statement: | As an end user, I want to have a profile setting for cruises so that I can easily view available cruise packages
Acceptance Criteria: | • Provide a profile option to view cruise vacations • Display a list of available cruise packages • Each cruise page will display the following: • The port the cruise will depart from • The ports the cruise will stop at • The length of the cruise • Link to take user to purchase page of the listed cruise

## User Story Details #3
User Story Number: | 5
User Story Name: | Price limit filter
User Story Size: | Small
User Story Value Statement: | As an end user, I want to have a filter for price limits so that I can view vacation packages based on a specific budget
Acceptance Criteria: | • Provide a filter within the search page to display vacation packages in a specified price limit • Price limit filter will allow for serches: • Below $999 • Between $1000-$1499 • Between $1500-$1999 • Above $2000